## RABillBrowse_projwise6388360806
Project RA Bill
SPAN TRIDENT
Bill Date From 24/03/2000 To 24/05/2025
Page 1 of 1
Total Records: 42 Records 1 To 42
Project | WO NO | RABill Sr.No | RA Bill Date | Cont Bill No | Contractor | Executed_By | Voucher_No | TASK | Labour_Name | Qty | Unit | Rate | PS % | Retention_Amt | Total_RetRelease | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Total Amount | Status | Credits | Debits | TDS_Amt | Due Date
SPAN TRIDENT | 5 | 28 | 25 Feb 2025 | SSLDL/2024-25/3 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 235 | SHORE PILING WORK 800 MM Dia. 24 mtr | 800 MM Dia Piles Boring | 260.55 | RMT | 1950 | 100 | 0 | 0 | 508072.5 | C + S GST 18% IP | 91453.06 | 599525.56 | 599525.56 | Approved | 0 | 0 | 0 | 25 Feb 2025
SPAN TRIDENT | 5 | 28 | 25 Feb 2025 | SSLDL/2024-25/3 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 235 | SHORE PILING WORK 800 MM Dia. 24 mtr | Chiselling in Rock for Socketing | 65.7 | Hrs | 1000 | 100 | 0 | 0 | 65700 | C + S GST 18% IP | 11826 | 77526 | 77526 | Approved | 0 | 0 | 0 | 25 Feb 2025
SPAN TRIDENT | 5 | 28 | 25 Feb 2025 | SSLDL/2024-25/3 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 235 | SHORE PILING WORK 800 MM Dia. 24 mtr | Mud Removing Charges | 47 | Trip | 3200 | 100 | 0 | 0 | 150400 | C + S GST 18% IP | 27072 | 177472 | 177472 | Approved | 0 | 0 | 0 | 25 Feb 2025
SPAN TRIDENT | 5 | 28 | 25 Feb 2025 | SSLDL/2024-25/3 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 235 | SHORE PILING WORK 800 MM Dia. 24 mtr | RMC Concrete Charges | 260.55 | RMT | 300 | 100 | 0 | 0 | 78165 | C + S GST 18% IP | 14069.7 | 92234.7 | 92234.7 | Approved | 0 | 0 | 0 | 25 Feb 2025
SPAN TRIDENT | 5 | 28 | 25 Feb 2025 | SSLDL/2024-25/3 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 235 | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Fabricating, Lifting & Lowering Steel | 6.38 | MT | 5500 | 100 | 0 | 0 | 35090 | C + S GST 18% IP | 6316.2 | 41406.2 | 41406.2 | Approved | 0 | 0 | 0 | 25 Feb 2025
SPAN TRIDENT | 9 | 26 | 01 Nov 2024 | BE-43 | Bhakti Enterprise | Bhakti Enterprise | JV - 157 | Site Cleaning | Debrage Cleaning | 4 | Brass | 1500 | 100 | 0 | 0 | 6000 | C + S GST 18% IP | 1080 | 7080 | 7080 | Approved | 0 | 0 | 0 | 01 Nov 2024
SPAN TRIDENT | 9 | 26 | 01 Nov 2024 | BE-43 | Bhakti Enterprise | Bhakti Enterprise | JV - 157 | Site Cleaning | JCB Service | 2 | Day | 8000 | 100 | 0 | 0 | 16000 | C + S GST 18% IP | 2880 | 18880 | 18880 | Approved | 0 | 0 | 0 | 01 Nov 2024
SPAN TRIDENT | 9 | 25 | 22 Dec 2024 | BE-51 | Bhakti Enterprise | Bhakti Enterprise | JV - 156 | Site Cleaning | Debrage Cleaning | 20 | Brass | 1500 | 100 | 0 | 0 | 30000 | C + S GST 18% IP | 5400 | 35400 | 35400 | Approved | 0 | 0 | 0 | 22 Dec 2024
SPAN TRIDENT | 9 | 25 | 22 Dec 2024 | BE-51 | Bhakti Enterprise | Bhakti Enterprise | JV - 156 | Site Cleaning | Debrage Cleaning | 16 | Brass | 1500 | 100 | 0 | 0 | 24000 | C + S GST 18% IP | 4320 | 28320 | 28320 | Approved | 0 | 0 | 0 | 22 Dec 2024
SPAN TRIDENT | 9 | 25 | 22 Dec 2024 | BE-51 | Bhakti Enterprise | Bhakti Enterprise | JV - 156 | Site Cleaning | JCB Service | 1 | Day | 8000 | 100 | 0 | 0 | 8000 | C + S GST 18% IP | 1440 | 9440 | 9440 | Approved | 0 | 0 | 0 | 22 Dec 2024
SPAN TRIDENT | 9 | 24 | 10 Dec 2024 | BE-49 | Bhakti Enterprise | Bhakti Enterprise | JV - 155 | Site Cleaning | Debrage Cleaning | 16 | Brass | 1500 | 100 | 0 | 0 | 24000 | C + S GST 18% IP | 4320 | 28320 | 28320 | Approved | 0 | 0 | 0 | 10 Dec 2024
SPAN TRIDENT | 9 | 24 | 10 Dec 2024 | BE-49 | Bhakti Enterprise | Bhakti Enterprise | JV - 155 | Site Cleaning | JCB Service | 1 | Day | 8000 | 100 | 0 | 0 | 8000 | C + S GST 18% IP | 1440 | 9440 | 9440 | Approved | 0 | 0 | 0 | 10 Dec 2024
SPAN TRIDENT | 9 | 24 | 10 Dec 2024 | BE-49 | Bhakti Enterprise | Bhakti Enterprise | JV - 155 | Site Cleaning | Debrage Cleaning | 4 | Brass | 1500 | 100 | 0 | 0 | 6000 | C + S GST 18% IP | 1080 | 7080 | 7080 | Approved | 0 | 0 | 0 | 10 Dec 2024
SPAN TRIDENT | 4 | 21 | 26 Mar 2025 | KA/24-25/02 | KASTUREE ASSOCIATES | KASTUREE ASSOCIATES | JV - 154 | 4th SLAB | Labours for CIVIL-RCC Work | 2944.672 | Sq.ft | 1066.79 | 100 | 47120.2 | 0 | 3141346.64 | C + S GST 18% IP | 565442.4 | 3706789.04 | 3706789.04 | Approved | 0 | 0 | 0 | 26 Mar 2025
SPAN TRIDENT | 4 | 21 | 26 Mar 2025 | KA/24-25/02 | KASTUREE ASSOCIATES | KASTUREE ASSOCIATES | JV - 154 | 3rd SLAB | Labours for CIVIL-RCC Work | 2944.672 | Sq.ft | 1066.79 | 100 | 47120.2 | 0 | 3141346.64 | C + S GST 18% IP | 565442.4 | 3706789.04 | 3706789.04 | Approved | 0 | 0 | 0 | 26 Mar 2025
SPAN TRIDENT | 1 | 20 | 15 Mar 2025 | 590 | Shri Krishna Clinic | Shri Krishna Clinic | JV - 152 | Doctor Health Checkup | Medical Health Checkup | 2 | No. | 1750 | 100 | 0 | 0 | 3500 | C + S GST 0% URD | 0 | 3500 | 3500 | Approved | 0 | 0 | 0 | 15 Mar 2025
SPAN TRIDENT | 1 | 20 | 15 Mar 2025 | 590 | Shri Krishna Clinic | Shri Krishna Clinic | JV - 152 | Doctor Health Checkup | Medical Health Checkup | 2 | No. | 1750 | 100 | 0 | 0 | 3500 | C + S GST 0% URD | 0 | 3500 | 3500 | Approved | 0 | 0 | 0 | 15 Mar 2025
SPAN TRIDENT | 8 | 19 | 07 Jan 2025 | 2489 | SAI RAJ WATER SUPPLY | SAI RAJ WATER SUPPLY | JV - 144 | Water Supply Services | Water Tanker Freight | 26 | Trip | 1000 | 100 | 0 | 0 | 26000 | C + S GST 0% URD | 0 | 26000 | 26000 | Approved | 0 | 0 | 0 | 07 Jan 2025
SPAN TRIDENT | 8 | 18 | 07 Jan 2025 | 2488 | SAI RAJ WATER SUPPLY | SAI RAJ WATER SUPPLY | JV - 143 | Water Supply Services | Water Tanker Freight | 34 | Trip | 1000 | 100 | 0 | 0 | 34000 | C + S GST 0% URD | 0 | 34000 | 34000 | Approved | 0 | 0 | 0 | 07 Jan 2025
SPAN TRIDENT | 8 | 17 | 06 Dec 2024 | 2447 | SAI RAJ WATER SUPPLY | SAI RAJ WATER SUPPLY | JV - 142 | Water Supply Services | Water Tanker Freight | 3 | Trip | 1000 | 100 | 0 | 0 | 3000 | C + S GST 0% URD | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 06 Dec 2024
SPAN TRIDENT | 8 | 16 | 06 Dec 2024 | 2446 | SAI RAJ WATER SUPPLY | SAI RAJ WATER SUPPLY | JV - 141 | Water Supply Services | Water Tanker Freight | 35 | Trip | 1000 | 100 | 0 | 0 | 35000 | C + S GST 0% URD | 0 | 35000 | 35000 | Approved | 0 | 0 | 0 | 06 Dec 2024
SPAN TRIDENT | 2 | 15 | 31 Mar 2025 | INV-000128 | Classic City Pest Control Private Limited | Classic City Pest Control Private Limited | JV - 70 | Pest Control Services | Pest Control Anti Larval Spray Treatment | 12 | No. | 1400 | 100 | 0 | 0 | 16800 | C + S GST 18% IP | 3024 | 19824 | 19824 | Approved | 0 | 0 | 0 | 31 Mar 2025
SPAN TRIDENT | 2 | 15 | 31 Mar 2025 | INV-000128 | Classic City Pest Control Private Limited | Classic City Pest Control Private Limited | JV - 70 | Pest Control Services | Pest Control Fogging | 12 | No. | 1100 | 100 | 0 | 0 | 13200 | C + S GST 18% IP | 2376 | 15576 | 15576 | Approved | 0 | 0 | 0 | 31 Mar 2025
SPAN TRIDENT | 6 | 14 | 31 Mar 2025 | RVFS/993/2025 | RIGHT VALUE FACILITY SERVICS | RIGHT VALUE FACILITY SERVICS | JV - 58 | MISC. SERVICES Security Guard Services | Security Guard Services | 2 | Month | 9000 | 100 | 0 | 0 | 18000 | C + S GST 0% URD | 0 | 18000 | 18000 | Approved | 0 | 0 | 0 | 31 Mar 2025
SPAN TRIDENT | 6 | 13 | 28 Feb 2025 | RVFS/125/2025 | RIGHT VALUE FACILITY SERVICS | RIGHT VALUE FACILITY SERVICS | JV - 57 | MISC. SERVICES Security Guard Services | Security Guard Services | 2 | Month | 9000 | 100 | 0 | 0 | 18000 | C + S GST 0% URD | 0 | 18000 | 18000 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 6 | 12 | 31 Jan 2025 | RVFS/907/2025 | RIGHT VALUE FACILITY SERVICS | RIGHT VALUE FACILITY SERVICS | JV - 56 | MISC. SERVICES Security Guard Services | Security Guard Services | 2 | Month | 9000 | 100 | 0 | 0 | 18000 | C + S GST 0% URD | 0 | 18000 | 18000 | Approved | 0 | 0 | 0 | 31 Jan 2025
SPAN TRIDENT | 1 | 8 | 25 Mar 2025 | 553 | Shri Krishna Clinic | Shri Krishna Clinic | JV - 19 | Doctor Health Checkup | Medical Health Checkup | 2 | No. | 1750 | 100 | 0 | 0 | 3500 | C + S GST 0% URD | 0 | 3500 | 3500 | Approved | 0 | 0 | 0 | 04 Feb 2025
SPAN TRIDENT | 5 | 7 | 21 Feb 2025 | SSLDL/2024-25/2 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 17 | SHORE PILING WORK 800 MM Dia. 24 mtr | 800 MM Dia Piles Boring | 283.85 | RMT | 1950 | 100 | 0 | 0 | 553507.5 | C + S GST 18% IP | 99631.36 | 653138.86 | 653138.86 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 7 | 21 Feb 2025 | SSLDL/2024-25/2 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 17 | SHORE PILING WORK 800 MM Dia. 24 mtr | Chiselling in Rock for Socketing | 71.05 | Hrs | 1000 | 100 | 0 | 0 | 71050 | C + S GST 18% IP | 12789 | 83839 | 83839 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 7 | 21 Feb 2025 | SSLDL/2024-25/2 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 17 | SHORE PILING WORK 800 MM Dia. 24 mtr | Mud Removing Charges | 49 | Trip | 3200 | 100 | 0 | 0 | 156800 | C + S GST 18% IP | 28224 | 185024 | 185024 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 7 | 21 Feb 2025 | SSLDL/2024-25/2 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 17 | SHORE PILING WORK 800 MM Dia. 24 mtr | RMC Concrete Charges | 283.85 | RMT | 300 | 100 | 0 | 0 | 85155 | C + S GST 18% IP | 15327.9 | 100482.9 | 100482.9 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 7 | 21 Feb 2025 | SSLDL/2024-25/2 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 17 | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Fabricating, Lifting & Lowering Steel | 6.96 | MT | 5500 | 100 | 0 | 0 | 38280 | C + S GST 18% IP | 6890.4 | 45170.4 | 45170.4 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | 800 MM Dia Piles Boring | 333.3 | RMT | 1950 | 100 | 0 | 0 | 649935 | C + S GST 18% IP | 116988.3 | 766923.3 | 766923.3 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | Chiselling in Rock for Socketing | 87.1 | Hrs | 1000 | 100 | 0 | 0 | 87100 | C + S GST 18% IP | 15678 | 102778 | 102778 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | Mud Removing Charges | 41 | Trip | 3200 | 100 | 0 | 0 | 131200 | C + S GST 18% IP | 23616 | 154816 | 154816 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | RMC Concrete Charges | 333.3 | RMT | 300 | 100 | 0 | 0 | 99990 | C + S GST 18% IP | 17998.2 | 117988.2 | 117988.2 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Fabricating, Lifting & Lowering Steel | 7.688 | MT | 5500 | 100 | 0 | 0 | 42284 | C + S GST 18% IP | 7611.12 | 49895.12 | 49895.12 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 5 | 6 | 21 Feb 2025 | SSLDL/2024-25/1 | Harshleen Enterprise LLP | Harshleen Enterprise LLP | JV - 16 | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Mobilization At Site | 1 | No. | 50000 | 100 | 0 | 0 | 50000 | C + S GST 18% IP | 9000 | 59000 | 59000 | Approved | 0 | 0 | 0 | 28 Feb 2025
SPAN TRIDENT | 4 | 5 | 05 Feb 2025 | KA/24-25/01 | KASTUREE ASSOCIATES | KASTUREE ASSOCIATES | JV - 22 | 1st SLAB BUILDING | Labours for CIVIL-RCC Work | 3635.398 | Sq.ft | 1066.79 | 100 | 58173.09 | 0 | 3878206.23 | C + S GST 18% IP | 698077.12 | 4576283.35 | 4576283.35 | Approved | 0 | 0 | 0 | 05 Feb 2025
SPAN TRIDENT | 4 | 5 | 05 Feb 2025 | KA/24-25/01 | KASTUREE ASSOCIATES | KASTUREE ASSOCIATES | JV - 22 | 2nd SLAB BUILDING | Labours for CIVIL-RCC Work | 3029.498 | Sq.ft | 1066.79 | 100 | 48477.57 | 0 | 3231838.17 | C + S GST 18% IP | 581730.88 | 3813569.05 | 3813569.05 | Approved | 0 | 0 | 0 | 05 Feb 2025
SPAN TRIDENT | 2 | 4 | 03 Feb 2025 | INV-000111 | Classic City Pest Control Private Limited | Classic City Pest Control Private Limited | JV - 14 | Pest Control Services | Pest Control Anti Larval Spray Treatment | 12 | No. | 1400 | 100 | 0 | 0 | 16800 | C + S GST 18% IP | 3024 | 19824 | 19824 | Approved | 0 | 0 | 0 | 05 Feb 2025
SPAN TRIDENT | 2 | 4 | 03 Feb 2025 | INV-000111 | Classic City Pest Control Private Limited | Classic City Pest Control Private Limited | JV - 14 | Pest Control Services | Pest Control Fogging | 12 | No. | 1100 | 100 | 0 | 0 | 13200 | C + S GST 18% IP | 2376 | 15576 | 15576 | Approved | 0 | 0 | 0 | 05 Feb 2025